## Sheet1
Material | Vendor | Country | Lead Time | PO Date | Required On Site Date | Delivery Date | Status
Elastic Pad | RailTech India | India | 60 | 2026-02-04 | 2026-04-05 | 2026-04-10 | Delayed - Delivered
MSS Pad | MetroFast Systems | Germany | 90 | 2026-02-07 | 2026-05-28 | 2026-06-11 | Delayed - Delivered
Tension Clamp | Global Track GmbH | China | 45 | 2026-02-10 | 2026-03-22 | 2026-04-19 | Delayed - Delivered
UIC 60 Rails | Shenzhen Rail Parts | Japan | 75 | 2026-02-13 | 2026-05-19 | 2026-06-02 | Delayed - Delivered
Fastening System | Nippon Weld | UAE | 35 | 2026-02-16 | 2026-03-18 | 2026-04-15 | Delayed - Delivered
Welding Consumables | InfraBuild UAE | South Korea | 75 | 2026-02-19 | 2026-05-15 | 2026-06-12 | Delayed - Delivered
Base Plate | Saini Engineering | India | 60 | 2026-02-22 | 2026-05-13 | 2026-05-13 | Delivered
Insulated Joint | Korea Transit Supply | Germany | 120 | 2026-02-25 | 2026-06-25 | 2026-06-17 | In Transit
Turnout Bearer | RailTech India | China | 35 | 2026-02-28 | 2026-04-04 | 2026-04-04 | Delivered
Check Rail | MetroFast Systems | Japan | 45 | 2026-03-03 | 2026-04-17 | 2026-05-15 | Delayed - Delivered
Cable Tray | Global Track GmbH | UAE | 75 | 2026-03-06 | 2026-05-20 | 2026-06-03 | Delayed - Delivered
OHE Mast | Shenzhen Rail Parts | South Korea | 90 | 2026-03-09 | 2026-06-27 | 2026-07-11 | Delayed - Delivered
Signalling Cable | Nippon Weld | India | 35 | 2026-03-12 | 2026-05-06 | 2026-05-06 | Delivered
Axle Counter | InfraBuild UAE | Germany | 60 | 2026-03-15 | 2026-05-09 |  | Delayed - Not Delivered
Rail Lubricator | Saini Engineering | China | 35 | 2026-03-18 | 2026-05-02 | 2026-05-16 | Delayed - Delivered
Grout | Korea Transit Supply | Japan | 90 | 2026-03-21 | 2026-07-09 | 2026-07-14 | Delayed - Delivered
Elastic Pad | RailTech India | UAE | 35 | 2026-03-24 | 2026-05-08 | 2026-04-30 | Delivered
MSS Pad | MetroFast Systems | South Korea | 120 | 2026-03-27 | 2026-08-14 | 2026-09-11 | Delayed - Delivered
Tension Clamp | Global Track GmbH | India | 60 | 2026-03-30 | 2026-06-08 |  | PO Released
UIC 60 Rails | Shenzhen Rail Parts | Germany | 35 | 2026-04-02 | 2026-05-17 | 2026-05-09 | Delivered
Fastening System | Nippon Weld | China | 120 | 2026-04-05 | 2026-08-13 | 2026-09-24 | Delayed - Delivered
Welding Consumables | InfraBuild UAE | Japan | 90 | 2026-04-08 | 2026-07-02 | 2026-07-02 | In Transit
Base Plate | Saini Engineering | UAE | 60 | 2026-04-11 | 2026-06-05 | 2026-06-19 | Delayed - Delivered
Insulated Joint | Korea Transit Supply | South Korea | 35 | 2026-04-14 | 2026-05-29 | 2026-05-21 | Delivered
Turnout Bearer | RailTech India | India | 120 | 2026-04-17 | 2026-08-25 | 2026-08-17 | In Transit
Check Rail | MetroFast Systems | Germany | 90 | 2026-04-20 | 2026-07-29 | 2026-08-12 | Delayed - Delivered
Cable Tray | Global Track GmbH | China | 35 | 2026-04-23 | 2026-05-28 | 2026-06-25 | Delayed - Delivered
OHE Mast | Shenzhen Rail Parts | Japan | 120 | 2026-04-26 | 2026-09-03 | 2026-09-08 | Delayed - Delivered
Signalling Cable | Nippon Weld | UAE | 35 | 2026-04-29 | 2026-06-03 |  | Delayed - Not Delivered
Axle Counter | InfraBuild UAE | South Korea | 90 | 2026-05-02 | 2026-07-26 | 2026-07-26 | In Transit
Rail Lubricator | Saini Engineering | India | 90 | 2026-05-05 | 2026-07-29 | 2026-08-26 | Delayed - Delivered
Grout | Korea Transit Supply | Germany | 35 | 2026-05-08 | 2026-06-07 | 2026-06-21 | Delayed - Delivered
Elastic Pad | RailTech India | China | 60 | 2026-05-11 | 2026-07-05 | 2026-07-05 | In Transit
MSS Pad | MetroFast Systems | Japan | 45 | 2026-05-14 | 2026-06-28 | 2026-06-28 | In Transit
Tension Clamp | Global Track GmbH | UAE | 90 | 2026-05-17 | 2026-08-10 | 2026-08-15 | Delayed - Delivered
UIC 60 Rails | Shenzhen Rail Parts | South Korea | 75 | 2026-05-20 | 2026-08-23 | 2026-09-20 | Delayed - Delivered
Fastening System | Nippon Weld | India | 35 | 2026-05-23 | 2026-07-07 | 2026-07-21 | Delayed - Delivered
Welding Consumables | InfraBuild UAE | Germany | 75 | 2026-05-26 | 2026-08-04 | 2026-07-27 | In Transit
Base Plate | Saini Engineering | China | 90 | 2026-05-29 | 2026-08-27 | 2026-09-24 | Delayed - Delivered
Insulated Joint | Korea Transit Supply | Japan | 90 | 2026-06-01 | 2026-08-25 |  | PO Released
Turnout Bearer | RailTech India | UAE | 90 | 2026-06-04 | 2026-09-12 | 2026-10-10 | Delayed - Delivered
Check Rail | MetroFast Systems | South Korea | 60 | 2026-06-07 | 2026-08-26 |  | PO Released
Cable Tray | Global Track GmbH | India | 35 | 2026-06-10 | 2026-07-15 | 2026-07-15 | In Transit
OHE Mast | Shenzhen Rail Parts | Germany | 120 | 2026-06-13 | 2026-10-11 | 2026-10-11 | In Transit
Signalling Cable | Nippon Weld | China | 60 | 2026-06-16 | 2026-09-04 |  | PO Released
Axle Counter | InfraBuild UAE | Japan | 120 | 2026-06-19 | 2026-11-06 | 2026-10-29 | In Transit
Rail Lubricator | Saini Engineering | UAE | 45 | 2026-06-22 | 2026-08-26 | 2026-09-09 | Delayed - Delivered
Grout | Korea Transit Supply | South Korea | 75 | 2026-06-25 | 2026-09-08 | 2026-09-08 | In Transit