## Sheet1
Open RFI | Closed RFI | Open NCR | Closed NCR | Inspection Status
14 | 126 | 5 | 42 | Track plinth inspections ongoing; welding NCR ageing visible
9 | 88 | 3 | 31 | Depot works inspections acceptable with minor shuttering observations
11 | 74 | 4 | 28 | Material inspection reports pending for fastening lot 3
6 | 63 | 2 | 19 | Systems installation quality stable