## Sheet1
Risk ID | Description | Probability | Impact | Risk Score | Owner | Mitigation
R-001 | Access Delay at depot interface | 4 | 5 | 20 | Project Manager | Daily constraint log and escalation to corridor director
R-002 | ROW Delay near station approach | 3 | 5 | 15 | Planning Engineer | Expedite approval package with decision due dates
R-003 | Material Delay for fastening system | 5 | 2 | 10 | Contracts Engineer | Alternative vendor and buffer stock review
R-004 | Design Delay on plinth interface | 5 | 3 | 15 | Procurement Lead | Recovery schedule with resequenced work fronts
R-005 | Subcontractor Performance below baseline | 3 | 4 | 12 | QA/QC Manager | Dedicated task force with weekly PMO review
R-006 | Weather disruption to concreting | 3 | 5 | 15 | Construction Manager | Daily constraint log and escalation to corridor director
R-007 | Client approvals cycle exceeds SLA | 5 | 4 | 20 | Client Interface | Expedite approval package with decision due dates
R-008 | Utility diversion obstruction | 2 | 3 | 6 | Project Manager | Alternative vendor and buffer stock review
R-009 | Rail delivery customs hold | 4 | 5 | 20 | Planning Engineer | Recovery schedule with resequenced work fronts
R-010 | FBW machine availability | 4 | 3 | 12 | Contracts Engineer | Dedicated task force with weekly PMO review
R-011 | NCR recurrence in welding | 4 | 4 | 16 | Procurement Lead | Daily constraint log and escalation to corridor director
R-012 | Testing slot conflict with systems contractor | 4 | 3 | 12 | QA/QC Manager | Expedite approval package with decision due dates
R-013 | Access Delay at depot interface | 4 | 4 | 16 | Construction Manager | Alternative vendor and buffer stock review
R-014 | ROW Delay near station approach | 5 | 3 | 15 | Client Interface | Recovery schedule with resequenced work fronts
R-015 | Material Delay for fastening system | 4 | 5 | 20 | Project Manager | Dedicated task force with weekly PMO review
R-016 | Design Delay on plinth interface | 2 | 5 | 10 | Planning Engineer | Daily constraint log and escalation to corridor director
R-017 | Subcontractor Performance below baseline | 4 | 2 | 8 | Contracts Engineer | Expedite approval package with decision due dates
R-018 | Weather disruption to concreting | 3 | 4 | 12 | Procurement Lead | Alternative vendor and buffer stock review
R-019 | Client approvals cycle exceeds SLA | 2 | 4 | 8 | QA/QC Manager | Recovery schedule with resequenced work fronts
R-020 | Utility diversion obstruction | 3 | 4 | 12 | Construction Manager | Dedicated task force with weekly PMO review
R-021 | Rail delivery customs hold | 2 | 5 | 10 | Client Interface | Daily constraint log and escalation to corridor director
R-022 | FBW machine availability | 5 | 5 | 25 | Project Manager | Expedite approval package with decision due dates
R-023 | NCR recurrence in welding | 4 | 3 | 12 | Planning Engineer | Alternative vendor and buffer stock review
R-024 | Testing slot conflict with systems contractor | 4 | 2 | 8 | Contracts Engineer | Recovery schedule with resequenced work fronts
R-025 | Access Delay at depot interface | 2 | 3 | 6 | Procurement Lead | Dedicated task force with weekly PMO review
R-026 | ROW Delay near station approach | 4 | 5 | 20 | QA/QC Manager | Daily constraint log and escalation to corridor director
R-027 | Material Delay for fastening system | 4 | 4 | 16 | Construction Manager | Expedite approval package with decision due dates
R-028 | Design Delay on plinth interface | 3 | 5 | 15 | Client Interface | Alternative vendor and buffer stock review
R-029 | Subcontractor Performance below baseline | 3 | 4 | 12 | Project Manager | Recovery schedule with resequenced work fronts
R-030 | Weather disruption to concreting | 3 | 5 | 15 | Planning Engineer | Dedicated task force with weekly PMO review
R-031 | Client approvals cycle exceeds SLA | 4 | 3 | 12 | Contracts Engineer | Daily constraint log and escalation to corridor director
R-032 | Utility diversion obstruction | 2 | 4 | 8 | Procurement Lead | Expedite approval package with decision due dates
R-033 | Rail delivery customs hold | 4 | 3 | 12 | QA/QC Manager | Alternative vendor and buffer stock review
R-034 | FBW machine availability | 5 | 3 | 15 | Construction Manager | Recovery schedule with resequenced work fronts
R-035 | NCR recurrence in welding | 3 | 5 | 15 | Client Interface | Dedicated task force with weekly PMO review
R-036 | Testing slot conflict with systems contractor | 3 | 4 | 12 | Project Manager | Daily constraint log and escalation to corridor director