## Sheet1
Milestone | Planned Date | Forecast Date | Actual Date | Owner | Status
Depot access handed over | 2026-03-06 | 2026-03-06 | 2026-03-03 | Planning | Completed
Viaduct civil front released | 2026-03-20 | 2026-03-27 | 2026-03-25 | Track | Completed
Survey control accepted | 2026-04-03 | 2026-04-10 | 2026-04-13 | Systems | Completed
First ballastless track plinth complete | 2026-04-17 | 2026-05-01 | 2026-04-17 | Depot | Completed
Rail delivery lot 1 on site | 2026-05-01 | 2026-05-01 | 2026-05-11 | QA/QC | Completed
Fastening system lot 1 on site | 2026-05-15 | 2026-06-19 | 2026-05-25 | Client | Completed
First FBW weld accepted | 2026-05-29 | 2026-05-29 |  | Contracts | On Track
Track linking Ch 0-2 km complete | 2026-06-12 | 2026-07-17 |  | Planning | At Risk
Track linking Ch 2-5 km complete | 2026-06-26 | 2026-07-03 |  | Track | At Risk
Depot track slab complete | 2026-07-10 | 2026-08-27 |  | Systems | At Risk
Turnout 1 commissioned | 2026-07-24 | 2026-07-24 |  | Depot | On Track
OHE interface ready | 2026-08-07 | 2026-09-11 |  | QA/QC | At Risk
Signalling cable route clear | 2026-08-21 | 2026-09-11 |  | Client | At Risk
Mainline track geometry approved | 2026-09-04 | 2026-09-25 |  | Contracts | At Risk
Ultrasonic testing complete | 2026-09-18 | 2026-10-09 |  | Planning | At Risk
Power energisation permit | 2026-10-02 | 2026-10-23 |  | Track | At Risk
Static testing start | 2026-10-16 | 2026-10-30 |  | Systems | At Risk
Dynamic testing start | 2026-10-30 | 2026-10-30 |  | Depot | On Track
Trial run start | 2026-11-13 | 2026-11-13 |  | QA/QC | On Track
Safety certification package submitted | 2026-11-27 | 2027-01-01 |  | Client | At Risk
Punch list below threshold | 2026-12-11 | 2026-12-25 |  | Contracts | At Risk
Depot commissioning complete | 2026-12-25 | 2027-01-15 |  | Planning | At Risk
Mainline commissioning complete | 2027-01-08 | 2027-01-15 |  | Track | At Risk
Revenue readiness certificate | 2027-01-22 | 2027-01-22 |  | Systems | On Track